## Sheet1
Module | Feature | User Functionality | MoSCoW | Release Phase
Registration | Register using email/phone/house no | Launch Application (Web Or Mobile) | Must Have | MVP
|  | Registration | Must Have | MVP
|  | OTP | Must Have | MVP
|  | Verification | Must Have | MVP
|  | Confirmation | Must Have | MVP
Authentication | OTP/email verification | Launch Application | Must Have | MVP
|  | Registration | Must Have | MVP
|  | Receives OTP | Must Have | MVP
|  | Enter OTP | Must Have | MVP
|  | Post Registration | Must Have | MVP
Resident Management | Edit own profile, Log complaints or requests, Add visitor details | Edit Own Profile | Must Have | MVP
|  | Log Complaint or Service Request | Must Have | MVP
|  | Add Visitor Details | Should Have | V1.1
Community Management | Notice Board | Admins can post notices, updates, and emergency alerts. | Must Have | MVP
|  | Residents can view and acknowledge notices. | Could Have | V1.3
| Event Management | Admins or designated users can create community events. | Could Have | Future
|  | Residents can RSVP, share with others, and receive reminders. | Should Have | V1.1
| Polls & Surveys | Create polls on community topics. | Could Have | Future
|  | Residents vote anonymously or openly, based on admin settings. | Could Have | Future
| Forums/Groups | Residents join or create discussion groups. | Could Have | Future
|  | Admins can moderate content. | Could Have | Future
| Resident Directory | Searchable list of residents by flat/unit. | Could Have | Future
| Community Gallery | Upload and browse event photos and videos. | Could Have | Future
|  | Content curated by admin. | Could Have | Future
Service Provider Management | Service Provider Directory | Admins can create and manage a directory of authorized vendors | Should Have | V1.1
|  | (electricians, plumbers, etc.); residents can browse and contact them. | Should Have | V1.1
| Vendor Onboarding | Admins can onboard vendors via a step-by-step form including KYC, | Must Have | MVP
|  | services offered, TAT, and SLA terms | Must Have | MVP
| Contract Management | Maintain digital records of service contracts, | Should Have | V1.3
|  | renewal dates, service level terms, and pricing agreements. | Should Have | V1.3
| Performance Rating System | Residents and admins can rate and review service providers | Could Have | Future
|  | based on timeliness, quality, and professionalism. | Could Have | Future
| Scheduling & Time Slots | Residents can request specific time slots for services. | Should Have | V1.3
|  | Admin or vendor can approve/reject and manage bookings. | Should Have | V1.3
| Service Request Management | Residents can raise service requests via app; | Must Have | MVP
|  | requests are auto-assigned or manually routed to the right vendor. | Must Have | MVP
| Check-In & Check-Out Logs | Every vendor/service provider logs check-in | Should Have | V1.1
|  | Check-out via QR, RFID, or manual input. | Should Have | V1.1
| Attendance & Roster | Daily/weekly roster for contract staff (cleaners, gardeners, etc.); | Should Have | V1.3
|  | attendance tracked via biometric or app-based check-in. | Should Have | V1.3
| Rate Card Management | Define per-service or per-hour pricing for vendors. | Could Have | Future
|  | Residents and admins can view pricing before approval. | Could Have | Future
| Compliance & KYC Tracking | System stores vendor KYC documents and tracks expiry dates for | Could Have | Future
|  | licenses, insurances, or background checks. | Could Have | Future
| Payment Integration | Allow residents to pay service providers directly through the app, | Must Have | MVP
|  | or admins to process payments for common-area services. | Must Have | MVP
| Dispute Resolution System | Admins can mediate service issues. Residents or vendors | Could Have | Future
|  | can raise tickets to flag service issues or payment disputes. | Could Have | Future
| Recurring Services Setup | Admins/residents can set up auto-renewal services | Should Have | V1.3
|  | (e.g., weekly housekeeping, biweekly water tank cleaning). | Should Have | V1.3
| Geo-Fencing for Vendors | Vendors can only operate within defined boundaries | Won’t Have | Future
|  | (specific buildings or wings). | Won’t Have | Future
| Work Order Management | Admins can raise and assign work orders for AMC | Could Have | Future
|  | (Annual Maintenance Contracts), repairs, replacements, etc. | Could Have | Future
| Service Provider App Panel | Mobile interface for vendors to view assigned tasks, | Should Have | V1.3
|  | update job status, check payment status, and manage their team. | Should Have | V1.3
| Task Completion Verification | Residents or admins can verify job completion via OTP, | Should Have | V1.3
|  | photo proof, or feedback form. | Should Have | V1.2
Financial Management | Maintenance Billing | Generate and share periodic (monthly/quarterly) | Must Have | MVP
|  | maintenance bills with residents. | Must Have | MVP
| Payment Gateway Integration | Residents can pay bills online via UPI, net banking, cards, or wallets. | Must Have | MVP
|  |  | Must Have | MVP
| Invoice & Receipt Management | Generate GST-compliant invoices and | Must Have | MVP
|  | auto-generate receipts post-payment. | Must Have | MVP
| Ledger & Account Statement | Each resident can view their individual ledger— | Should Have | V1.1
|  | past payments, dues, fines, etc. | Should Have | V1.1
| Defaulter Management | Track unpaid or overdue accounts. | Must Have | MVP
|  | Send reminders and generate penalty notices. | Must Have | MVP
| Penalty & Discount Settings | Admins can define late payment penalties or early bird discounts. | Should Have | v1.1
| Expense Tracking | Record and categorize society expenses | Should Have | V1.1
|  | records expenses for staff salaries, repairs, utilities | Should Have | V1.1
| Budgeting & Forecasting | Set annual budgets for different categories. | Could Have | Future
|  | Monitor overspending or underutilization. | Could Have | Future
| Vendor Payments | Pay service providers (e.g., cleaners, electricians) | Could Have | Future
|  | via system after work verification. | Could Have | Future
| Annual Reports Generation | Auto-generate financial summaries including income, | Should Have | V1.1
|  | expenses, and fund balance for AGM or audits. | Should Have | V1.1
| SMS/Email Reminders | System sends payment reminders, receipt confirmations, | Should Have | V1.1
|  | or defaulter notices via SMS and email. | Should Have | V1.1
| Payment Status Dashboard | Graphical dashboard showing real-time payment collection %, | Must Have | MVP
|  | unpaid dues, and top defaulters. | Must Have | MVP
| Income Categories | Categorize all income sources | Could Have | Future
Security Management | Visitor Passes | Generate visitor passes for guests | Should Have | V1.2
|  | Login/Authentication | Should Have | V1.2
|  | Create Visitor Pass | Should Have | V1.2
|  | Select Time Slot | Should Have | V1.2
|  | Generate Pass | Should Have | V1.2
|  | Share Pass | Should Have | V1.2
|  | View/Cancel Pass | Should Have | V1.2
| Receive emergency alerts | Receive emergency alerts via mobile notifications | Must Have | MVP
|  | Receive Notification | Must Have | MVP
|  | Emergency Type Display | Must Have | MVP
|  | Emergency Instructions | Must Have | MVP
|  | Acknowledge Alert (optional) | Must Have | MVP
|  | Multi-Channel Backup | Must Have | MVP
|  | Historical Alerts (optional) | Must Have | MVP
| CCTV/Camera Access | View camera feed (if allowed) for own block/area | Won’t Have | Future
|  | Login and Authentication | Won’t Have | Future
|  | Camera Access Authorization | Won’t Have | Future
|  | Live Feed Streaming | Won’t Have | Future
|  | Camera List UI | Won’t Have | Future
|  | View Details (optional) | Won’t Have | Future
|  | Access Logs (optional) | Won’t Have | Future
| Guest Access | Temporary passes for guests | Should Have | V1.2
|  | Create Guest Pass | Should Have | V1.2
|  | Set Validity | Should Have | V1.2
|  | QR Code Generation | Should Have | V1.2
|  | Send to Guest | Should Have | V1.2
|  | Track Pass Status | Should Have | V1.2
|  | Cancel/Modify Pass | Should Have | V1.2
|  | History View | Should Have | V1.2
| Time Slot Management | View or select valid time slots for visitor access | Could Have | Future
|  | View Available Time Slots | Could Have | Future
|  | Book a Slot | Could Have | Future
|  | Modify/Cancel Booking | Could Have | Future
|  | Receive Reminders | Could Have | Future
|  | Track Slot Usage | Could Have | Future
|  | Slot Restrictions | Could Have | Future
User Interface & User Experience | Dashboard | Personalized dashboard showing services, | Must Have | MVP
|  | View Personalized Dashboard | Must Have | MVP
|  | Alerts | Must Have | MVP
|  | Make Payments | Must Have | MVP
|  | Track Payments | Must Have | MVP
|  | Reorder/Customize Widgets (optional) | Must Have | MVP
|  | Dark Mode / Accessibility (optional) | Must Have | MVP
| Widgets | Use widgets for events, Alerts, Payments | Should Have | V1.3
|  | Events Widget | Should Have | V1.3
|  | Alerts Widget | Should Have | V1.3
|  | Payments Widget | Should Have | V1.3
|  | Widget Layout Control (optional) | Should Have | V1.3
| Service Tracking | Raise Service Request / Track | Must Have | MVP
|  | Raise Service Request | Must Have | MVP
|  | Track Request Status | Must Have | MVP
|  | Update or Cancel Request | Must Have | MVP
|  | Notifications | Must Have | MVP
| UI Customization | Use drag & drop widgets for dashboard personalization | Could Have | Future
|  | Enable Edit Mode | Could Have | Future
|  | Drag & Drop Widgets | Could Have | Future
|  | Add/Remove Widgets | Could Have | Future
|  | Save Custom Layout | Could Have | Future
|  | Restore to Default | Could Have | Future
|  | Sync Across Devices | Could Have | Future
Integration & API | App/Device Integration | Connect with smart home devices (if supported) | Won’t Have | Future
|  | Link Smart Devices | Won’t Have | Future
|  | App Access Control | Won’t Have | Future
|  | Real-Time Device Sync | Won’t Have | Future
|  | Unlink Devices | Won’t Have | Future
|  | Integration Log View (Optional) | Won’t Have | Future
| API Access | No direct interaction with APIs by residents. | Won’t Have | Future
| Support Needs | Raise tech support tickets if integration fails | Must Have | MVP
|  | View service disruption alerts | Must Have | MVP
|  | Report issue (via app, optional) | Must Have | MVP
| Third-Party Access | Use authorized apps | Could Have | Future
|  | Request access for specific third-party (optional) | Could Have | Future
|  | Receive status updates or alerts | Could Have | Future
|  | Block/unblock specific vendors (optional) | Could Have | Future