## Sheet1
RACI Matrix - Residential Township Management System
Task/Deliverable | Project Manager | Business Analyst | Developer | QA Tester | Client (Society Head) | Designer | Security Vendor
Gather Requirements | I | R/A |  |  | C |  | C
Draft BRD & FRD | I | R/A |  |  | C | C | I
UI/UX Design | I | C |  |  | C | R/A
Admin Panel Module Development | I | C | R/A |  | I
Resident Registration & Login Module | I | C | R/A |  | I | C
Complaint Management Module | I | C | R |  | C | C
Payment Integration | I | C | R/A |  | C
Service Provider Onboarding Module | I | C | R |  | C |  | C
Security & Visitor Management Module | I | C | R |  | C |  | A/R
Testing and QA | I | C | R | A/R | I |  | I
Client UAT & Feedback | I | C |  | R | A/R |  | I
Final Deployment | A/R | C | R | R | I |  | I